GLOBAL GENERATIVE AI DEVELOPERS SUMMIT 2026

Master Event Strategy & Orchestration Plan

Date: 2026-06-25
Location: Bangalore
Guest Count: 150 attendees
Theme: AI & Technology
Budget Tier: 1-5L

# 1. Executive Summary

This document represents the synthesized planning portfolio for Global Generative AI Developers Summit 2026, scheduled to be hosted on 2026-06-25 in the vibrant hub of Bangalore. Orchestrated by a custom multi-agent cooperative network, this comprehensive brief aggregates venue scouting, speaker selection, menus, setup operations, logistics workflows, and communication pipelines into an actionable master deployment blueprint. Our primary objective is to cultivate an immersive, seamless, and high-impact experience tailored specifically to the 'AI & Technology' community, welcoming approximately 150 distinguished guests within a 1-5L budget framework.

Key Planning Directives: • Scale: 150 attendees, requiring appropriate safety, seating, and caterer capacity. • Dietary Provisions: Accommodating Vegetarian, Gluten-Free. • Domain Target: Theme set to 'AI & Technology', guiding speaker outreach, AV installations, and agendas.

# 2. Master Event Timeline

Below is the synchronized master schedule outlining critical stages, specific activities, and the designated teams/agents responsible for execution.

| Time Slot | Activity Detail | Responsible Party |
| --- | --- | --- |
| 08:00 AM - 09:30 AM | AV Set up, Soundcheck, and Banner Installation | Logistics Team & AV Vendor |
| 09:30 AM - 10:00 AM | Guest Registration, Welcome Drinks, & Badge Distribution | Logistics / Registration Desk |
| 10:00 AM - 10:15 AM | Opening Keynote & Event Theme Briefing | Lead Speaker & Host |
| 10:15 AM - 11:30 AM | Technical Presentation / Panel Discussion Session 1 | Speaker Panelists |
| 11:30 AM - 12:00 PM | Structured Coffee Break & Networking Session | Catering Vendor |
| 12:00 PM - 01:30 PM | Masterclass / Hands-on Interactive Session | Host & Invited Experts |
| 01:30 PM - 02:30 PM | Networking Lunch Buffet | Catering Vendor |
| 02:30 PM - 04:00 PM | Collaborative Team Work or Q&A Brainstorm Session | All Attendees & Facilitators |
| 04:00 PM - 04:30 PM | Closing Remarks, Certificate Distribution & Thank You | Host & Coordinator Agent |
| 04:30 PM - 06:00 PM | AV Tear-down, Venue Cleaning & Vendor Settlement | Logistics Team |

# 3. Vendor Briefing & Services

## 3.1 Venue Recommendations

The Venue Scouting Agent recommends the following properties tailored to host our guest checklist and safety protocols:

Option 1: Grand Corporate Plaza  |  Capacity: 150 attendees  |  Cost: ₹1,50,000 
Description: High-speed WiFi, modern AV setup, central location.

## 3.2 Catering Requirements

The Catering Planning Agent outlines requirements based on strict guest counts and preferences:

• Standard Fusion Buffet (₹850 per head):
  Includes: Continental starters, main course, traditional desserts.

# 4. Invited Speakers & Panels

The Speaker Agent has identified industry leading profiles aligned closely with 'AI & Technology':

1. Dr. Aris Thorne
Session Topic: "Next-Gen AI Agents"  |  Est. Honorarium: ₹50,000
Bio: Leading researcher in vector spaces and deep learning systems.

2. Elena Rostova
Session Topic: "SaaS Scaling Tactics"  |  Est. Honorarium: ₹35,000
Bio: Product Architect specializing in zero-latency serverless pipelines.

# 5. Operations & Logistics Checklist

The Logistics Agent has organized operational checklists based on standard Asana milestone structures:

## On-Ground Setup

[  ]  Verify dual mic system & AV mixer channels

[  ]  Confirm projector compatibility and HDMI connectivity

[  ]  Install backdrops, badges, signages & directional banners

## Transport & Security

[  ]  Arrange airport shuttle for key speakers

[  ]  Ensure registration counter has digital list and printing backups

[  ]  Setup designated first-aid post and emergency routes

# 6. Communication Pack

Copy-paste ready communications drafted by the Communications Agent: